Group Weekly Activities

Thursday, August 20, 2026

7:30 PM

Group Weekly Rhythm (Wed–Tue cycle)

| Days | Focus | What Happens |
| --- | --- | --- |
| Wed–Sat | Learn & Apply | Watch the week's assigned courses, take notes - write three lines for each topic n sub topics , and complete in-course exercises. As each course wraps up, move straight into that hands-on practice tasks |
| Sat-Sun | Catch-Up & Consolidate | No new material. Use this time to finish anything left over from Wed–Sat, revisit weak spots, and practice how to express these topics to others - to deepen understanding. |
| Mon/Tue | Group Workshop | Come together with the group to walk through what everyone learnt. built, compare approaches, troubleshoot blockers, and get feedback before starting the next week's material. |

Why this order works

- Wed–Sat (4 days): front-loads the learning while energy and focus are highest, and keeps practice right next to the course it came from so it sticks.

- Sun–Mon (2 days): a built-in buffer — nobody finishes exactly on schedule, so this absorbs slippage instead of letting it snowball into next week.

- Mon/Tue (1 day): closes the loop socially. Explaining your work to peers (and seeing how others solved the same task differently) cements the week far better than solo review alone.

For the group workshop day specifically

- Each person does a 15–20 min walkthrough of their courses, explains to others, shows work and their practice tasks (ex: dashboard, test suite, API, backlog, etc.)

- Peers ask "why did you do it that way?" — this surfaces gaps faster than any quiz

- Facilitator (or a rotating volunteer) collects common blockers and folds fixes into the next week's plan

Instructions for Each Member

1. Set Up the Shared Team Git Repository Create a Git repository for your team (if one doesn't already exist) with the following top-level folders:

- business-analyst

- developer

- tester

- data-analyst

- report-writer

2. Migrate Your Existing Work Move all your previous role-based materials from your old personal/role Git folder into the new team repository:

- Go into the folder matching your role (e.g., tester/ if you're a Tester)

- Inside it, create a folder with your name

- Copy in all your Week 1–5 work from your old folder

- Commit and push this migration as your first commit in the team repo

From this point forward, all your future work — course notes, practice files, task outputs — gets committed and pushed into your folder (<role>/<your-name>/), not the old individual repo.

3. Complete the Shared Tasks First Before moving on to anything role-specific, make sure every team member has completed the common/shared tasks assigned to the whole group. Iteration -1 Tasks (for all members)

4. Commit Your Work Regularly As you complete both the shared tasks and your practice work, commit and push to your dedicated folder in the team repo. Commit often — don't wait until the end of the week to push everything at once.

5. Move on to Role-Specific Tasks Once the shared tasks are done and committed, proceed to the tasks specific to your role (see the list below). Role Based Tasks List

Iteration -1 Tasks (for all members)

| # | Tool | Course Title | Source | Link |
| --- | --- | --- | --- | --- |
| 1 | JIRA | Learning Jira (Cloud Edition) | LinkedIn Learning | Open |
| 1 | JIRA | Learning Jira Software | LinkedIn Learning | Open |
| 1 | JIRA | Jira: Basic Administration | LinkedIn Learning | Open |
| 2 | Confluence | Confluence Topic Hub (pages, blogs, tables, search) | LinkedIn Learning | Open |
| 2 | Confluence | Learning Confluence Administration | LinkedIn Learning | Open |
| 3 | Visio | Visio 2019 Essential Training | LinkedIn Learning | Open |
| 4 | Draw.io | Make Effective Flowcharts with draw.io / diagrams.net | YouTube | Open |
| 5 | Trello | Trello Essential Training | LinkedIn Learning | Open |
| 6 | Microsoft Planner | Microsoft Planner Essential Training | LinkedIn Learning | Open |
| 7 | OneNote | OneNote Essential Training | LinkedIn Learning | Open |
| 8 | Microsoft Office Suite | Getting Started with Microsoft 365 (path) | LinkedIn Learning | Open |
| 8 | Microsoft Office Suite | Working Smarter with Microsoft 365 (path) | LinkedIn Learning | Open |
| 9 | Outlook | Outlook Essential Training (Microsoft 365) | LinkedIn Learning | Open |
| 9 | Teams | Microsoft Teams Topic Hub | LinkedIn Learning | Open |
| 10 | Git | Git Essential Training | LinkedIn Learning | Open |
| 10 | GitHub | GitHub Essential Training: 1 The Basics | LinkedIn Learning | Open |
| 10 | GitHub | Learning Git and GitHub | LinkedIn Learning | Open |
| 10 | Bitbucket | (Use Git skills above — Bitbucket UI, same commands) | Search youtube and understand basics |  |
| 11 | SharePoint & OneDrive | Bundled in Microsoft 365 paths above (rows 8) | LinkedIn Learning | Open |
| 12 | Power BI | Power BI Essential Training | LinkedIn Learning | Open |
| 12 | Power BI | Learning Power BI Desktop | LinkedIn Learning | Open |
| 12 | Power BI | PL-300 Certification Path | LinkedIn Learning | Open |
| 13 | Lucidchart | Getting Started in Lucidchart in Under 5 Minutes | YouTube | Open |
| 13 | Lucidchart | Lucidchart: Advanced Visual Diagrams for Beginners | YouTube | Open |
| 14 | Microsoft Forms | Microsoft Forms Essential Training | LinkedIn Learning | Open |
| 14 | Microsoft Forms | Microsoft Forms Tutorial | YouTube | Open |
| 15 | Excel | Bundled in Getting Started with Microsoft 365 (row 8) | LinkedIn Learning | Open |
| 16 | Notepad++ | Notepad++ Tutorial for Beginners | YouTube | Open |
| 16 | Notepad++ | Notepad++ Tips and Tricks | YouTube | Open |
| 17 | PowerShell | PowerShell 7 Essential Training | LinkedIn Learning | Open |
| 17 | PowerShell | Learning PowerShell Core | LinkedIn Learning | Open |
| 18 | Batch Script | Batch Scripting Tutorial for Beginners | YouTube | Open |
| 18 | Batch Script | Learn Full CMD in One Video (70+ Commands) | YouTube | Open |

ROLE BASED TASKS (will be updated every week)

1. Business Analyst (BA)

Week 1 — Requirements & Domain Foundations

Course

Business Analysis Foundations

Business Analysis: Gathering and Documenting Requirements

Agile Requirements Foundations

Practice: Pick a real app you use daily (e.g., a food delivery app). Write a 1-page Business Requirements Document (BRD) and 5 user stories with acceptance criteria for one feature (e.g., "reorder past meal").

Week 2 — Process Modeling & Tools

Course

Learning BPMN (Business Process Model and Notation)

Learning Visio (or Lucidchart Essential Training)

SQL Essential Training (BAs must read data, not just request it)

Practice: Model the "reorder past meal" process as a BPMN flowchart. Write 5 SQL SELECT queries against a sample database (use a free sample DB like Northwind) to answer business questions like "top 5 customers by order value."

Week 3 — Stakeholder Management & Delivery

Course

Business Analysis: Managing Stakeholder Expectations

Agile Product Owner: Managing the Product Backlog

Jira Essential Training

Practice: Create a mock backlog in a free Jira board for your Week 1 feature — write epics, break into stories, prioritize, and run a 15-min mock sprint planning session (record yourself or present to a friend).

2. Data Analyst

Week 1 — Core Analytical Tools

Course

SQL Essential Training

Excel: Advanced Formulas and Functions

Statistics Foundations: 1

Practice: Download a adventure works db (search and download). Write 10 SQL queries covering JOINs, GROUP BY.

3. Report Analyst

Week 1 — Reporting Fundamentals

Course

Excel: Advanced Formulas and Functions

SQL Essential Training

Learning Power BI

Practice: Take the Superstore (or any) dataset and build a static Excel report with pivot tables + pivot charts answering 5 stakeholder questions.

4. Tester (QA)

Week 1 — Manual Testing Foundations

Course

Software Testing Foundations: Fundamentals

Software Testing Foundations: Test Techniques

Agile Testing

Practice: Pick any public website/app. Write a test plan and 15 manual test cases (functional, negative, boundary) for one feature (e.g., login form). Log 3 intentional "bugs" you find in a free tool like Trello or a bug-tracker template.

Week 2 — Automation Basics

Course

Selenium Essential Training

Learning Test Automation

API Testing Foundations

Practice: Automate 5 of your Week 1 manual test cases using Selenium (Java or Python). Separately, use Postman to write 5 API test requests (GET/POST) against a free public API (e.g., reqres.in), asserting status codes and response fields.

Week 3 — CI/CD & Test Management

Course

Jenkins for Developers/Testers (or Learning DevOps: CI/CD)

Jira Essential Training

Software Testing: Bug Reports and Test Cases

Practice: Push your Selenium tests to a GitHub repo, and set up a free GitHub Actions workflow to run them automatically on push. Log all bugs found across the 3 weeks into a Jira board with severity/priority tagged.

5. Full Stack .NET Developer

Week 1 — Language & Backend Foundations

Course

C# Essential Training

.NET Core Essential Training

SQL Server Essential Training

Practice: Build a console app in C# that connects to a local SQL Server (or SQLite) database and performs CRUD operations on a simple "Tasks" table.

Week 2 — Web API & Frontend Basics

Course

ASP.NET Core: Building RESTful APIs

Entity Framework Core Essential Training

React.js Essential Training (or Angular Essential Training, pick one)

Practice: Turn your console CRUD app into a full ASP.NET Core Web API (with Entity Framework). Build a minimal React/Angular frontend that lists, adds, and deletes tasks by calling your API.

Week 3 — Full Stack Integration & Deployment

Course

ASP.NET Core: MVC

Learning Docker

Azure Fundamentals (AZ-900 prep)

Practice: Containerize your API with Docker, and deploy the full app (API + frontend) to a free tier on Azure App Service or Render. Write a short README documenting setup, architecture, and how to run it locally.